## Slide 1: Project Management
INTERSECT – Bootcamp 2023
David Rumph

## Slide 2: What is Project Management?
Definition:
  Project management is the use of specific knowledge, skills, tools and techniques to deliver something of value to people. The development of software for an improved business (or scientific) process, the construction of a building (or scientific instrument), the relief effort after a natural disaster, the expansion of sales into a new geographic market—these are all examples of projects.
    (from Project Management Institute website)

## Slide 3: Who needs project management (PM)?
If a group of people are working together, some amount of project management methodology will help
  How large, long and complex the project is will determine how much project management discipline will be helpful
  Generally, the more time and/or people involved, the more PM helps
If you’re writing scripts for your own research to test out some ideas, and the project will extend some time, you (and ”future you”) will probably benefit from some PM
If you’re trying something out for just this week, you probably don’t need project management
  But are you sure it’s really just “this week”?

## Slide 4: Phases of a Software Project
[Most of] the phases of software development:
  Determine software requirements
  Software design
  Implementation
  Software testing
  Software documentation
  Release/deploy the software to the customer
  Ongoing maintenance
These phases can be mixed, or (sometimes) reordered
  Line between requirements and design is often blurry
  Implementation, testing and user docs often proceed concurrently
  Test Driven Development (TDD): Tests are written first
Definition of roles vary
  E.g. the “customer” or “user” may also be the author of the software, or may be quite removed

## Slide 5: Software Development Process?
[Most of] the phases of software development:
  Determine software requirements
  Software design
  Implementation
  Software testing
  Software documentation
  Release/deploy the software to the customer
  Ongoing maintenance
Idea: try to complete each phase before the next phase begins
  Generally referred to as the waterfall model
  Each phase produces specific deliverables, which feed into the next phase
  “Progress flows downwards through the phases, like a waterfall.”
Notes: Who has heard of “the waterfall model” ?
If so, what was the context?

## Slide 6: The Waterfall Model
Each phase produces artifacts that feed into the next phase
  Assumption: each phase’s artifacts are actually correct!
Ideally, each phase will also identify any issues/flaws in the previous phase
  Iterate between phases to fix issues
Software
Requirements
Software
Design
Implementation
Testing
Release/Deploy
Requirements Specification
Project Code
Test Code
Build Process
Installer
Test Results
Operations
Software Design Specification
Requirements Traceability Matrix
Development Schedule
Notes: Forward-only waterfall is usually only used as a straw-man to belittle waterfall-style approaches.
Most of the time, waterfall includes the feedback mechanism to iterate between stages.

## Slide 7: The Waterfall Model: In Real Life
A much more common scenario: miscommunication of software requirements!
  May not be identified until client demos, or formal acceptance testing
In traditional waterfall models, the client is often only involved in requirements phase, and in acceptance-testing or later phases
Software
Requirements
Software
Design
Implementation
Testing
Requirements Specification
Project Code
Test Code
Build Process
Installer
Test Results
Operations
Software Design Specification
Requirements Traceability Matrix
Development Schedule
Release/Deploy
Notes: Arrow goes from “Testing” to “Software Requirements” because of demos / acceptance testing. Typically, developers will not know that they are not satisfying the requirements.

## Slide 8: The Waterfall Model: In Real Life
In this case, very significant amounts of work may need to be reviewed, revised or discarded
It’s 50x to 200x less expensive to get a requirement right in the first place, than to fix a requirement after implementation
  Boehm and Papaccio, 1988
Software
Requirements
Software
Design
Implementation
Testing
Release/Deploy
Requirements Specification
Project Code
Test Code
Build Process
Installer
Test Results
Operations
Software Design Specification
Requirements Traceability Matrix
Development Schedule

## Slide 9: The Waterfall Model
When does the waterfall model work well?
Waterfall model works well when:
  Software requirements are very clear, well understood, and unchanging
  Technical implementation details are also very well understood
  (Generally considered more suited to manufacturing, but this is also changing with rapid prototyping!)
Inversely, waterfall model works terribly when these things aren’t present, greatly exceeding time and financial budgets
Software
Requirements
Software
Design
Implementation
Testing
Release/Deploy
Requirements Specification
Project Code
Test Code
Build Process
Installer
Test Results
Operations
Software Design Specification
Requirements Traceability Matrix
Development Schedule

## Slide 10: Software Development Methodologies
Waterfall-based models don’t handle lack of knowledge, or change, very effectively
  Poorly understood or changing software requirements
  Poorly understood technology or architecture choices
  (Lack of software-engineering discipline kills virtually all approaches)
At the other end of the spectrum are agile methodologies
  These methodologies are optimized to deal with poorly understood and/or changing requirements during development
  Also tend to incorporate other practices to improve software quality
Started becoming more popular in mid 1990s, as issues with waterfall approach became more and more evident

## Slide 11: The Agile Manifesto (2001)
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
https://agilemanifesto.org/
Notes: It can’t be overstated that there is value in the items on the right!
Sometimes people think that “agile” means “don’t plan; don’t document anything; just code.” Nothing could be further from the truth.

## Slide 12: Core Value of Agile
(Nearly) everything about Agile Development is based on one value:
Identify and eliminate sources of WASTE

## Slide 13: Individuals and Interactions over Processes and Tools
Good processes and tools are important, but it’s more important to make sure that people are happy, productive and communicating
If a process or tool isn’t working for people, change it!
Agile methods favor lightweight, widely accessible tools over fancy, expensive software packages
  e.g. whiteboards in public areas
  e.g. simple text formats like markdown and restructuredText for documents
Agile methods promote a sustainable pace for software development
  i.e. a pace that can be sustained indefinitely; no heroics

## Slide 14: Individuals and Interactions over Processes and Tools (2)
Agile methods incorporate very regular communication of status, identification of issues, and retrospectives/postmortems on efforts
  Preferably face-to-face interactions
  A common approach:
    Daily interactions between software developers
    Planning and retrospectives every 1-4 weeks
Agile methods also respect the time of individuals
  Meetings are time-boxed so that software developers can focus on the problems they are solving
  e.g. daily status meetings time-boxed to 15 minutes
  e.g. planning meetings time-boxed to 1 hour per week of development effort

## Slide 15: Working Software over Comprehensive Documentation
Requirements specifications and design documents have one main purpose: to help get to useful, working software
  Customers generally don’t care about them once they have their software!
Agile methods generally maintain only documentation that allows the project to be developed, used and maintained, and no more
  A common agile approach: “just barely enough” documentation
  Focus on what developers can’t easily figure out looking at the code: the “big picture,” and “why?” rather than “what?”
  Do work “at the latest responsible moment”
    Guards against wasted work from changing requirements
Agile methods generally use lightweight representations for software requirements, UI designs, software architecture/design, etc.
  e.g. a whiteboard sketch of a UI workflow or domain model
  e.g. a 3x5 card with a brief user story described on it
  e.g. GitHub Issues to capture feature requests as well as bugs
Notes: A similar concept: Plan or design things at the “latest responsible moment.” Don’t be irresponsible, but don’t expend time and effort on things that may not actually be required.

## Slide 16: Customer Collaboration over Contract Negotiation
“Contract negotiation” means: “Give me a specification of what you want, then leave me alone so I can go get it done.”
  Can occur between team members, as well as between a team and its client
  Tends to make processes less flexible and adaptable to change
Agile expects requirements, or the understanding of requirements, to change!
  Encourages constant collaboration within teams, and between developers and clients, to ensure that everyone’s needs and goals are being met
  Some agile approaches do limit opportunities to change requirements to reduce “requirements churn”
Notes: This slide leads to the next slide: ”Constant collaboration allows you to identify when your understanding of the requirements isn’t correct, or when the design won’t work, etc. Which means you identify the need to make a change as early as possible.”

## Slide 17: Responding to Change over Following a Plan
When requirements change, the current plan may no longer be the right plan
Agile methods adapt to change by reviewing and revising plans iteratively, over short time periods
Agile methods tend to only have detailed plans for the short- to medium-term
  It doesn’t make sense to devise detailed plans for the long-term, if circumstances are likely to change
  If [when] changes come, any effort spent on detailed long-term plans would have been wasted
Notes: “Plan or design at the latest responsible moment.”

## Slide 18: Scrum
Scrum (and variants) is one of the most widely used agile methodologies
Initial phase: project envisioning
  How long this takes depends on the scope of the project
    May be as much as 2-4 weeks
At a high level, the client and the team define the following:
  A project vision – what the project is intended to accomplish
    No longer than a few pages at most, and often much shorter
  A project backlog – a list of key features to be implemented
    In envisioning, the features tend to be high-level and broad
    Typically expressed as “User Stories”
    Future efforts will refine the details
  An initial roadmap – a series of releases that include features in the backlog
    The first release should be the “Minimal Viable Product”

## Slide 19: Sprints
After project envisioning is completed, development occurs in a series of time-boxed iterations (1 week to 4 weeks) called sprints or iterations
Sprints start with a planning meeting, time-boxed to 1 hour per week
  e.g. for a 4-week sprint, the planning meeting may be no longer than 4 hours
The developers choose features from the project backlog to be implemented in the sprint
  Larger features are decomposed into smaller features; details are discussed
  Feature priority is determined by the client and the team, based on relevance to the product roadmap, risk/uncertainty, level of difficulty, etc.
    (“MoSCoW” – stay tuned!)
  Implementation cost is determined by the developers
The developers commit to completing those tasks within the sprint

## Slide 20: From Sprint to Sprint
At the end of the sprint is a sprint demo, and a retrospective
  Tends to be a short meeting, or is first part of next sprint’s planning meeting
Completed work is demonstrated to the client / stakeholders
  Agile places high priority on working software, and on customer collaboration
Everyone discusses lessons learned in the sprint
  What unexpected issues had to be dealt with, and what was learned
  What can be done better in future sprints
A sprint may include releasing/deploying software, or it may not
  Depends on where the team is with respect to the product roadmap

## Slide 21: Agile vs. Waterfall
Agile does requirements gathering and design incrementally, mostly just before implementation
Overall, may be more costly than a well-executed waterfall approach, as long as requirements and design don’t change!
Effort
Project Lifetime
requirements
(waterfall)
design
(waterfall)
sprints/iterations
requirements
and design (agile)

## Slide 22: Defining the Work
In scrum, the project backlog is the specification of what work remains to be done on the project
User stories – descriptions of features that can be implemented within a single sprint
Epics – features that will require multiple sprints to complete
  Epics contain user stories that correspond to the epic
Bugs – software defects encountered in completed work
Periodically, backlog grooming occurs
  Stories and epics that are no longer relevant to the project, are removed (e.g. because a requirement was later found to be unnecessary)
Notes: In literature, an “epic” is a long story!

## Slide 23: User Stories
Software features or capabilities from a user’s point of view
  Regular user
  Administrator
Written in “story” form:
  “As a user, I can view my data”
  “As a user, I can edit my data”
  “As an administrator, I can add a new user”
Non-functional requirements:
  “The system is robust against changes in the database format”
  “The system responds to a database commit in less than 50 ms”

## Slide 24: Kanban
Japanese for “Board”
A lightweight method for tracking work on a project
  Originally done using a board marked into four columns and Post-It notes
  Integrates well with GitHub
Best for small to medium size projects
Demo

## Slide 25: MoSCoW
A lightweight technique for prioritizing work
  Typically done in the sprint planning meeting
Focus is on the next software release/next sprint
  Must have
    Without this, we don’t have a useable release
  Should have
    The release would be less valuable or compelling without this, but would still be worth releasing
  Could have
    Nice to have, but not essential
  Won’t have
    Maybe not ever, but too much for this time
Work on Must Haves
Work on Should Haves if there is time remaining in the sprint

## Slide 26: Hands-On: Setup
MoSCoW
  Use your GitHub repo from yesterday’s “Issues Tracking” session
  Add Issue labels for “Must have”, “Should have”, “Could have” and “Won’t have”
Kanban
  Create a Kanban project board

## Slide 27: Hands-On
Sprint Planning
  In a group of about four:
    Create a Work Backlog based on these User Stories, expressed as GitHub issues
    Rate your issues for the “next” sprint using MoSCoW
  Individually:
    Populate the Work Backlog section with all of your issues
    Move those rated “Must have” and “Should have” to “Ready to be Developed”
User Stories:
  As a user, I can display my image data using preexisting tools
  As a user, I can specify an input and an output file name
  As a user, if I don’t specify an output file name, a reasonable one is generated
  As a user, I can display “before” and “after” images such that I can easily see differences